## Sheet1
Image Validation Bugs List
ID | Bug Details | Status | Comment | Replies
Image Collection Validation Software:
1 | When application exits (by clicking on top right corner x), Visual Studio still seems to be in debugging mode. | Resolved
2 | "XML Output" link takes users to HTTP 404 error page. The "p" in the "Output" seems to be cut as well. The XML output should be a local file not a web record | Resolved | Now XML Output File Coming from azure storage account | Still Broken. The page takes you to 404 Error still
3 | Driver query should only query drivers that have OEM in the InfName WMI Element. SELECT * FROM Win32_PnPSignedDriver should be something like: SELECT * FROM Win32_PnPSignedDriver WHERE InfName LIKE OEM% We only want to compare OEM Drivers not drivers packaged with Microsoft Windows | Resolved
4 | When clicking on the record link it only brings up the Azure Web service. The link should navigate directly to that record | New Request | Please elaborate more on this. However this should be treated as change request, since it was not covered in original documents. If we missed in the document then please let us know.
5 | Windows 8 x64
| When running the Image Collection Tool on Windows 8 x64 an exception occurs after login. | In-Progress
6 | Force as Primary Model Record and Force as Primary Product should be checkboxes and not radio buttons. The user should be able to force the record to both be a primary model and product on the same record - | Resolved
Image Validation Client:
7 | Bypass the credential screen for the Client. Do not allow user name required. This account should not perform delete operation and should have read permission only. | New Request/Resolved | This New Request
8 | Remove empty Grids. Remove duplicate entries from within Grids. | Resolved | In this some new changes.
9 | The Client Validation tool should be a separate tool that requires no log-on. | New Request/Resolved | New request not covered in requirement doc.
10 | Multiple of entries of the same value over and over again | Resolved
Image Validation Web Admin:
11 | Show the added record in the dropdown within "Browse Computer Validation Record". This record should be the Product WMI Attribute. Only one unique value per Product in the database should show. | New Request/Resolved | This is new request, This type of functionality not mention in document.
12 | Duplicate records are allowed but one record can only be PrimaryProduct and one can be PrimaryModel. A single record can be both primarmodel and primaryproduct then any other of that same model can’t be either. | Resolved | One system have two record, if 1st record has both IsPrimaryModel & IsPrimaryProduct are false and 2nd record has both are true that time both record are display OR Not (one with true)
13 | QuickSearch
| 1. If blank, return all available records. | Resolved
| 2. Allow for * search. | Resolved
| 3. Ignore case sensitive. CF-53 and cf-53 should return same results. | Resolved
14 | File and Folder
| 1. Allow for folder selection. Currently it only allows you to choose a file. Also even when a file is chosen it doesn’t save the full path in display only the file name | New Request | there is no any option to select folder in document & pdf screenshots.
| 2. The drive should be set to C:\ and after submitting a file it shows up as D:\ this will cause problems during validation | In-Progress
15 | Computer and Information
| 1. Formatting could be enhanced so the value lines up with the name. Currently in both Chrome and IE the information is overlapping and not formatted correctly. | Resolved
| 2. Serial Number is showing blank on several screens |  | Please let me know,which field you have point. This type of field not in database schema & also document. You have mention this field under computer info but this field not mention in collection tool.
16 | Hotfixes
| 1. There is no way to save IsRequired field. An update button or event must be used to save the checkbox state. | Resolved
17 | Add User
| 1. Under role “temp” is listed. Can this be removed? | Resolved
More Issues Found During Last Meeting (Testing tool)
| 1. Application, Driver & Hotfixes repeating entry (same item) to database again and again. | Resolved
| 2. One system has maximum two records in azure database. | Resolved
| 3. Issues with “Primary Records Force Option” under collection tool. | Resolved
Note/Queries:
Add user
1. How to send user information to user after creation account by admin?
Computer Info/Client tool
2. Serial Number : Which field you point for this?
Driver Information & Application Information
3. Please let me know, what's the mean of "OEM Version, Image Version" under driver & application?
4. Which type of url bind for "DownLoad Link" under Image validation Client?
SetUp Projects
5. What is your software distribution way (Make DVD OR DownLoad From Internet)?

## BugList_March14
Image Validation Bugs List
ID | Bug Details | Status | Comment | Test #1
1 | SSL Development to secure sites | Earlier Request |  | Please provide estimate
Image Validation Web Admin:
2 | File and Folder
| 1. Allow for folder selection. Currently it only allows you to choose a file. Also even when a file is chosen it doesn’t save the full path in display only the file name | New Request | there is no any option to select folder in document & pdf screenshots. | Please refer to Web_Administration_Portal spec page 34
| 2. The drive should be set to C:\ and after submitting a file it shows up as D:\ this will cause problems during validation | In-Progress
| 3. File & Folder site is crashing | New |  | Browsing through the site crashes it after a while
3 | Application Validator
| 1. Application matcher returns all apps as mismatch | New